## Sheet1
Project Stage | Task | Assigned to: | Notes | Date of Completion | Deadline | Reason for Delay(optional) | Git Commit tag
Requirement Generation | SPI Requirements | Andrew | Signed off by: Eric | 2020-05-12 | 2020-05-12 |  | N/A, See Teams folder | Completion Date Coloring Schema: | Deadline Coloring Schema:
| AXI Requirements | N/A | Signed off by: Eric | 2020-05-10 |  |  |  | Done before deadline | Done ahead of schedule
| Async/FIFO Requirements | Devon |  | 2020-05-12 |  |  |  | Done on day of deadline | Done on schedule
| Register Requirements | N/A |  | 2020-05-10 |  |  |  | Done with delay(reason required) | Done overdue
Design/Functionality Documents | SPI Functionality | Eric |  | 2020-05-12 | 2020-05-12 |  | N/A, See Teams folder | To Do | In progress
| AXI Functionality | Devon |  | 2020-05-12 |  |  |  | Overdue | Future deadline
| Async/FIFO Functionality | Devon/Eric |  | 2020-05-12
| Register Functionality | Andrew |  | 2020-05-12
Stage 1: AXI and Registers | Address select / Chip select | Andrew |  | 2020-05-14 | 2020-05-15 |  | 85a24b7
| FSM Setup for read/write | Eric |  | 2020-05-14 |  |  | ac60963
| Read Routine | Eric
| Write Routine | Andrew |  | 2020-05-15 |  |  | a1e5244
| Register Wrapper | Devon |  | 2020-05-18 |  | debugging submodules | 4f2a8a2
| Register submodules | Devon |  | 2020-05-15 |  |  | 9b24885
Stage 2: Async/FIFO and SPI | Parametrizable FIFO | Devon |  |  | 2020-05-21
| Signal Sync | Devon
| SPI Control Unit | Andrew
| Baud Rate Generator | Andrew |  | 2020-05-18 |  |  | bf22de0
| Shift register | Eric
| Slave SPI Interface | Eric
| Master SPI Interface | Andrew
Stage 3: Submodule Assembly | Project Wrapper | All |  |  | 2020-05-22
Stage 4: Functional Verification/Synthesis | Testbench creation |  |  |  | 2020-05-27
Simulation
STA analysis/adjustments
FPGA testing